## Ewaa plus test
Done
pending for dev phase
not done
Need to discuss
Need to review
Ewaa plus testing
S. No | Pages | Ewaa Team Remarks |  | Developers Remarks
|  | Remarks | comments | Remarks | comments
1 | Website Home page | Search Button drop down should be in english if english portal is on
Search Button is not working at the moment (error 404)
Contact us button has no function
Terms has no function till now
Job has no Function till now
no social media have any link
Generally Logo is on the corner and should be lil prominent
Help button is not working
4 | Sign in Page | There must be eye icon to show/hide your password (To be sure about the password)
|  | Forget password (no function) | send email and you entered email message and presson link to make new password
3 | Listing page | Standard information font color should be Gray
We must have some general information as mandatory entry
I can add picture but I cat delete pic (Problem in adding pic as I want to add multiple pics I can drag them at once but I cant post then one by one)
|  | I cant save and submit my listing (cant go beyound this step) | tested and it works
4 | Admin Control | Admin Control (Owner dashbaord) should b on when Admin login | I don’t to make another login for admin I know after login who is login if user or admin | seller when login go to dashboard seller
|  | Dashboard button for admin should be prominent on the side instead in between the tabs |  | make it at last li
5 | Forget password | Correct the content (Arabic and English)
|  | Password save function is not working | tested and it works
6 | Property Search | When we put some filter (It must show above that what a guest have searched) (like this he knows he activated the filter) |  | search input at search page drop down cant select from it
|  | There should be a way to disable the filter search |  | go to ads without parameters and check compunds number at this page
|  | in search there will b a country name as well or google map to target a location |  | add input called country as select at search page
7 | User Profile | When updating password it should be gone after saving
|  | Edit main informaiton (page should refresh by showing the edit information | values updated automaticly
|  | when I make any property as a listing page should refresh to main profile after posting | should go to confirm payment if I created if I updated I go to my profile
we
| Footer | Ewaa Plus Ewaa services allow you to rent, buy or sell a property while providing essential information to help you take one of life’s biggest financial decisions.